## Tasks
Pages Design | page_ID
Home Page
Blogger Registration
Blogger Home Page
Order Page

## Efforts
Task | Description | Task Owner | Start Date | End Date | Status | Actual Date | Remarks
BRD | Prepare complete detailed requirement document. | All | 2015-10-01 | 2015-10-05 | Completed | 2015-10-05 | Draft Version Completed
FSD |  | Haren | 2015-10-17 | 2015-10-22 | Pending
TSD |  | Haren | 2015-10-22 | 2015-10-31 | Pending
Pages Design | Few Pages design completed(home, blogger, ) | Avi | 2015-10-14 |  | Pending
Logo and Name | Draft version Name and Logo. (My Blogger) | Akshay/Avi | 2015-10-17 | 2015-10-30 | Pending
Pages Navigation | Complete chart for all the basic pages and there flow. () | Avi |  |  | Pending
Documentation | FSD, TSD, Research Doc, Page Design etc. (YTU) | Akshay |  |  | Pending
Infrastructure | GIT Repository, IDE setup, server, Framework Design Databases, Schema Definition, domain name, email_id, whatsapp group | Haren/Akshay | 2015-10-17 | 2015-10-22 | 20% |  | For domain name and email no deadlines as of now.
Research | Indian compitors, Global compititors, Growth Rate, Revenue Plan. | Akshay | 2015-10-17 | 2015-10-22 | Pending
Validations |  | Avi | 2015-10-17 | YTD | Pending
Meeting Plan | 1. Daily Status Plan 2. Product Design(every Sunday and Wednesday) 3. Revenue Plan