## Efforts
Task | Description | Task Owner | Start Date | End Date | Status | Actual Date | Remarks
BRD | Prepare complete detailed requirement document. | All | 2015-10-01 | 2015-10-05 | Completed | 2015-10-05 | Draft Version Completed
FSD |  | Haren |  |  | Pending
TSD |  | Haren |  |  | Pending
Pages Design |  | Avi |  |  | Pending
Logo and Name |  | Akshay/Avi |  |  | Pending
Pages Navigation | Complete chart for all the basic pages and there flow. () | Avi |  |  | Pending
Documentation |  | Akshay |  |  | Pending
Infrastructure |  | Haren/Akshay |  |  | Pending
Research